## Sheet1
Template: Water Supply Projects.
| nameOfTheDistrict | division | block | noOfGPHQs | sourceSanctioned | sourceNotDone | dPRNotSubmitted | pWSSanctioned | tenderingNotDone | workorderNotIssued | notCompleted | secondndVillageSourceSanctioned | notDone
Sl No | Name of the District | Division | Block | No. of GPHQs | Source Sanctioned | Source not done | DPR not submitted | PWS Sanctioned | Tendering not done | Workorder not issued | Not Completed | 2nd Village Source sanctioned | Source Not Done
1 | Keonjhar | Anandpur | anandapur | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 5 | 4
2 | Keonjhar | Anandpur | ghasipura | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 5 | 4
3 | Keonjhar | Anandpur | ghatagaon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 8
4 | Keonjhar | Anandpur | harichandanpur | 3 | 3 | 1 | 2 | 1 | 2 | 3 | 3 | 8 | 4
5 | Keonjhar | Anandpur | saharapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1
6 | Angul | Angul | angul | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 15 | 14
7 | Angul | Angul | athamallik | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 13 | 11
8 | Angul | Angul | banarpal | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 9 | 7
9 | Angul | Angul | kishorenagar | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 7 | 7
10 | Angul | Angul | pallahara | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0
11 | Cuttack | Athagarh | athagarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
12 | Cuttack | Athagarh | narasinghpur | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
13 | Cuttack | Athagarh | tigiria | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0
14 | Balangir | Balangir | agalpur | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2
15 | Balangir | Balangir | balangir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Balangir | Balangir | bangomunda | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 8 | 8
17 | Balangir | Balangir | belpada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 7 | 7
18 | Balangir | Balangir | deogaon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
19 | Balangir | Balangir | gudvela | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
20 | Balangir | Balangir | khaparakhol | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 1 | 1
21 | Balangir | Balangir | loisingha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
22 | Balangir | Balangir | muribahal | 3 | 3 | 1 | 3 | 0 | 3 | 3 | 3 | 9 | 9
23 | Balangir | Balangir | patnagarh | 3 | 3 | 1 | 3 | 0 | 3 | 3 | 3 | 6 | 6
24 | Balangir | Balangir | puintala | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 7 | 7
25 | Balangir | Balangir | saintala | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 4 | 4
26 | Balangir | Balangir | titilagarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
27 | Balangir | Balangir | turekela | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Balasore | Balasore | bahanaga | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
29 | Balasore | Balasore | balasore | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 4 | 4
30 | Balasore | Balasore | baliapal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
31 | Balasore | Balasore | basta | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
32 | Balasore | Balasore | bhograi | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 5 | 0
33 | Balasore | Balasore | jaleswar | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 4 | 0
34 | Balasore | Balasore | khaira | 4 | 4 | 2 | 3 | 0 | 4 | 4 | 4 | 3 | 0
35 | Balasore | Balasore | nilagiri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
36 | Balasore | Balasore | oupada | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0
37 | Balasore | Balasore | remuna | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
38 | Balasore | Balasore | simulia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
39 | Balasore | Balasore | soro | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
40 | Bargarh | Bargarh | ambabhona | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
41 | Bargarh | Bargarh | attabira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
42 | Bargarh | Bargarh | barapali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
43 | Bargarh | Bargarh | bargarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
44 | Bargarh | Bargarh | bhatli | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
45 | Bargarh | Bargarh | bheden | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 5 | 5
46 | Bargarh | Bargarh | bijepur | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 5 | 5
47 | Bargarh | Bargarh | gaisilet | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 3 | 3
48 | Bargarh | Bargarh | jharbandha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
49 | Bargarh | Bargarh | padampur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | Bargarh | Bargarh | paikamal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
51 | Bargarh | Bargarh | rajbarasambar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
52 | Bargarh | Bargarh | sohela | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 12
53 | Mayurbhanj | Baripada | badsahi | 9 | 9 | 4 | 7 | 2 | 9 | 9 | 9 | 3 | 1
54 | Mayurbhanj | Baripada | bangiriposi | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 8 | 8
55 | Mayurbhanj | Baripada | baripada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
56 | Mayurbhanj | Baripada | betnoti | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 0
57 | Mayurbhanj | Baripada | g.b.nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
58 | Mayurbhanj | Baripada | kaptipada | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 14 | 11
59 | Mayurbhanj | Baripada | khunta | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 1
60 | Mayurbhanj | Baripada | kuliana | 5 | 5 | 5 | 5 | 0 | 5 | 5 | 5 | 9 | 7
61 | Mayurbhanj | Baripada | morada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1
62 | Mayurbhanj | Baripada | rasagovindapur | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 1
63 | Mayurbhanj | Baripada | samakhunta | 4 | 4 | 3 | 4 | 1 | 4 | 4 | 4 | 6 | 6
64 | Mayurbhanj | Baripada | saraskana | 4 | 4 | 1 | 4 | 3 | 4 | 4 | 4 | 7 | 7
65 | Mayurbhanj | Baripada | suliapada | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 4 | 0
66 | Mayurbhanj | Baripada | udala | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 2 | 2
67 | Ganjam | Berhampur | chatrapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | Ganjam | Berhampur | chikiti | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | Ganjam | Berhampur | digapahandi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | Ganjam | Berhampur | ganjam | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | Ganjam | Berhampur | khalikote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2
72 | Ganjam | Berhampur | patrapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Ganjam | Berhampur | sanakhemundi | 5 | 5 | 3 | 5 | 0 | 5 | 5 | 5 | 3 | 1
74 | Ganjam | Berhampur | sheragada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | Bhadrak | Bhadrak | bandaripokhari | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 3 | 2
76 | Bhadrak | Bhadrak | bant | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 8 | 8
77 | Bhadrak | Bhadrak | basudebpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
78 | Bhadrak | Bhadrak | bhadrak | 5 | 5 | 3 | 5 | 0 | 5 | 5 | 5 | 23 | 22
79 | Bhadrak | Bhadrak | dhamanagar | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 11 | 11
80 | Bhadrak | Bhadrak | tihidi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
81 | Ganjam | Bhanjanagar | aska | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
82 | Ganjam | Bhanjanagar | bellaguntha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | Ganjam | Bhanjanagar | bhanjanagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
84 | Ganjam | Bhanjanagar | buguda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
85 | Ganjam | Bhanjanagar | dharakote | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
86 | Ganjam | Bhanjanagar | jagannathprasad | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
87 | Ganjam | Bhanjanagar | k.s.nagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Ganjam | Bhanjanagar | polosara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
89 | Ganjam | Bhanjanagar | purusottampur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Ganjam | Bhanjanagar | surada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 3
91 | Khorda | Bhubaneswar | balipatna | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1
92 | Khorda | Bhubaneswar | banpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1
93 | Khorda | Bhubaneswar | begunia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | Khorda | Bhubaneswar | bhubaneswar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
95 | Khorda | Bhubaneswar | chilika | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2
96 | Khorda | Bhubaneswar | jatani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
97 | Khorda | Bhubaneswar | khordha | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 0
98 | Khorda | Bhubaneswar | tangi | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 5 | 5
99 | Boudh | Boudh | boudh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
100 | Boudh | Boudh | harabhanga | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 3
101 | Boudh | Boudh | kantamal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | Cuttack | Cuttack | banki | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Cuttack | Cuttack | banki-ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Cuttack | Cuttack | barang | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
105 | Cuttack | Cuttack | nischintakoili | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3
106 | Cuttack | Cuttack | salipur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1
107 | Cuttack | Cuttack | tangi-cdr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | Dhenkanal | Dhenkanal | bhuban | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
109 | Dhenkanal | Dhenkanal | gondia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 6
110 | Dhenkanal | Dhenkanal | hindol | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 16 | 11
111 | Dhenkanal | Dhenkanal | kamakhyanagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
112 | Dhenkanal | Dhenkanal | kankadahad | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 4 | 4
113 | Dhenkanal | Dhenkanal | odapada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12 | 10
114 | Dhenkanal | Dhenkanal | parjang | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2
115 | Dhenkanal | Dhenkanal | sadar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4
116 | Gajapati | Gajapati | kasinagar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
117 | Gajapati | Gajapati | mohana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11
118 | Gajapati | Gajapati | nuagada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
119 | Gajapati | Gajapati | rayagada | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
120 | Jagatsinghpur | Jagatsinghpur | balikuda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
121 | Jagatsinghpur | Jagatsinghpur | jagatsinghpur | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2
122 | Jagatsinghpur | Jagatsinghpur | kujanga | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
123 | Jagatsinghpur | Jagatsinghpur | raghunathpur | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
124 | Jagatsinghpur | Jagatsinghpur | tirtol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
125 | Jajpur | Jajpur | badachana | 10 | 10 | 0 | 9 | 1 | 9 | 10 | 10 | 15 | 13
126 | Jajpur | Jajpur | bari | 4 | 4 | 0 | 1 | 0 | 4 | 4 | 4 | 8 | 1
127 | Jajpur | Jajpur | binjharpur | 5 | 5 | 0 | 1 | 2 | 1 | 2 | 5 | 1 | 0
128 | Jajpur | Jajpur | dangadi | 6 | 6 | 2 | 2 | 2 | 4 | 6 | 6 | 14 | 12
129 | Jajpur | Jajpur | dasarathpur | 4 | 4 | 1 | 3 | 0 | 4 | 4 | 4 | 11 | 6
130 | Jajpur | Jajpur | dharmasala | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 5 | 14 | 7
131 | Jajpur | Jajpur | jajpur | 3 | 3 | 0 | 0 | 2 | 0 | 3 | 3 | 3 | 1
132 | Jajpur | Jajpur | korai | 5 | 5 | 0 | 0 | 4 | 3 | 5 | 5 | 6 | 3
133 | Jajpur | Jajpur | rasulpur | 4 | 4 | 1 | 0 | 4 | 1 | 4 | 4 | 5 | 3
134 | Jajpur | Jajpur | dasrathpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | Jharsuguda | Jharsuguda | jharsuguda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
136 | Jharsuguda | Jharsuguda | kirimira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
137 | Jharsuguda | Jharsuguda | kolabira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | Jharsuguda | Jharsuguda | laikera | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
139 | Jharsuguda | Jharsuguda | lakhanpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | Kalahandi | Kalahandi | bhawanipatna | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 16 | 16
141 | Kalahandi | Kalahandi | dharmagarh | 4 | 4 | 1 | 4 | 0 | 4 | 4 | 4 | 13 | 13
142 | Kalahandi | Kalahandi | jaipatna | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 19 | 19
143 | Kalahandi | Kalahandi | junagarh | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 27 | 27
144 | Kalahandi | Kalahandi | kalampur | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 6 | 6
145 | Kalahandi | Kalahandi | karlamunda | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 5
146 | Kalahandi | Kalahandi | kesinga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
147 | Kalahandi | Kalahandi | koksara | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 13 | 13
148 | Kalahandi | Kalahandi | lanjigarh | 6 | 6 | 5 | 6 | 0 | 6 | 6 | 6 | 21 | 21
149 | Kalahandi | Kalahandi | m.rampur | 4 | 4 | 2 | 4 | 0 | 4 | 4 | 4 | 8 | 8
150 | Kalahandi | Kalahandi | narla | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6
151 | Kalahandi | Kalahandi | th.rampur | 15 | 15 | 13 | 15 | 0 | 15 | 15 | 15 | 13 | 13
152 | Kendrapada | Kendrapada | aali | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 4
153 | Kendrapada | Kendrapada | derabis | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 1
154 | Kendrapada | Kendrapada | garadpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
155 | Kendrapada | Kendrapada | kendrapara | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0
156 | Kendrapada | Kendrapada | mahakalapada | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 0 | 0
157 | Kendrapada | Kendrapada | marshaghai | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
158 | Kendrapada | Kendrapada | pattamundai | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 3 | 3
159 | Kendrapada | Kendrapada | rajkanika | 3 | 3 | 0 | 3 | 0 | 3 | 3 | 3 | 2 | 2
160 | Kendrapada | Kendrapada | rajnagar | 5 | 5 | 0 | 5 | 0 | 5 | 5 | 5 | 2 | 1
161 | Keonjhar | Keonjhar | joda | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
162 | Keonjhar | Keonjhar | patna | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 3
163 | Keonjhar | Keonjhar | telkoi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9
164 | Koraput | Koraput | bandhugaon | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 4 | 4
165 | Koraput | Koraput | boipariguda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
166 | Koraput | Koraput | boriguma | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
167 | Koraput | Koraput | dasamantpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
168 | Koraput | Koraput | jeypore | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | Koraput | Koraput | koraput | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | Koraput | Koraput | kundra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
171 | Koraput | Koraput | lamtaput | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
172 | Koraput | Koraput | laxmipur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | Koraput | Koraput | nandapur | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 11 | 11
174 | Koraput | Koraput | narayanpatna | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
175 | Koraput | Koraput | semiliguda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
176 | Malkangiri | Malkangiri | chitrakonda | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 6
177 | Malkangiri | Malkangiri | kalimela | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2
178 | Malkangiri | Malkangiri | khairput | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
179 | Malkangiri | Malkangiri | korkunda | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
180 | Malkangiri | Malkangiri | malkangiri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
181 | Nabarangpur | Nabarangpur | chandahandi | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 3
182 | Nabarangpur | Nabarangpur | dabugam | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 2 | 1 | 1
183 | Nabarangpur | Nabarangpur | jharigam | 3 | 3 | 0 | 3 | 0 | 3 | 3 | 3 | 5 | 5
184 | Nabarangpur | Nabarangpur | kosagumuda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
185 | Nabarangpur | Nabarangpur | nabarangpur | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 0 | 0
186 | Nabarangpur | Nabarangpur | papadahandi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7
187 | Nabarangpur | Nabarangpur | raighar | 7 | 7 | 2 | 7 | 0 | 7 | 7 | 7 | 3 | 3
188 | Nabarangpur | Nabarangpur | tentulikhunti | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0
189 | Nabarangpur | Nabarangpur | umerkote | 6 | 6 | 2 | 6 | 0 | 6 | 6 | 6 | 9 | 8
190 | Nayagarh | Nayagarh | bhapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
191 | Nayagarh | Nayagarh | daspalla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
192 | Nayagarh | Nayagarh | gania | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
193 | Nayagarh | Nayagarh | khandapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
194 | Nayagarh | Nayagarh | nayagarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 11
195 | Nayagarh | Nayagarh | nuagaon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
196 | Nayagarh | Nayagarh | odagaon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16
197 | Nayagarh | Nayagarh | ranpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1
198 | Nayagarh | Nayagarh | nayagarh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | NUAPADA | NUAPADA | khariar | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 4 | 4
200 | NUAPADA | NUAPADA | komna | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 2
201 | NUAPADA | Nuapada | nuapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
202 | NUAPADA | NUAPADA | sinapalli | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0
203 | Phulbani | Phulbani | baliguda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
204 | Phulbani | Phulbani | chakapada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Phulbani | Phulbani | daringbadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
206 | Phulbani | Phulbani | g.udayagiri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | Phulbani | Phulbani | k.nuagaon | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 6 | 6
208 | Phulbani | Phulbani | khajuripada | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
209 | Phulbani | Phulbani | kotagarh | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 4
210 | Phulbani | Phulbani | phiringia | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 10 | 10
211 | Phulbani | Phulbani | phulbani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | Phulbani | Phulbani | raikia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
213 | Phulbani | Phulbani | tumudibandha | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 5 | 5
214 | PURI | PURI | astarang | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
215 | PURI | PURI | bramhagiri | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0
216 | PURI | PURI | gop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
217 | PURI | PURI | kakatpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
218 | PURI | PURI | krushnaprasad | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0
219 | PURI | PURI | nimapara | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 10 | 10
220 | PURI | PURI | pipili | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 4 | 4
221 | PURI | PURI | puri sadar | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1
222 | PURI | PURI | satyabadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
223 | Mayurbhanj | Rairangpur | bahalda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
224 | Mayurbhanj | Rairangpur | bijatala | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 4 | 4
225 | Mayurbhanj | Rairangpur | bisoi | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 6 | 6
226 | Mayurbhanj | Rairangpur | jamda | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 3 | 3
227 | Mayurbhanj | Rairangpur | karanjia | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0
228 | Mayurbhanj | Rairangpur | sukruli | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 2 | 2
229 | Mayurbhanj | Rairangpur | thakurmunda | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 3 | 3
230 | Mayurbhanj | Rairangpur | tiring | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0
231 | RAYAGADA | RAYAGADA | bissam cuttack | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0
232 | RAYAGADA | RAYAGADA | chandrapur | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 3
233 | RAYAGADA | RAYAGADA | gudari | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 2 | 3 | 3
234 | RAYAGADA | RAYAGADA | gunupur | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1
235 | RAYAGADA | RAYAGADA | kalyansinghpur | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0
236 | RAYAGADA | RAYAGADA | kolanara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
237 | RAYAGADA | RAYAGADA | muniguda | 4 | 4 | 3 | 3 | 0 | 3 | 4 | 4 | 4 | 4
238 | RAYAGADA | RAYAGADA | padmapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
239 | RAYAGADA | RAYAGADA | ramanguda | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 1
240 | RAYAGADA | RAYAGADA | rayagada | 3 | 3 | 1 | 1 | 0 | 2 | 2 | 3 | 9 | 4
241 | Sundargarh | Rourkela | bisra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
242 | Sundargarh | Rourkela | bonai | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
243 | Sundargarh | Rourkela | gurundia | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 4 | 4
244 | Sundargarh | Rourkela | koida | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 0 | 0
245 | Sundargarh | Rourkela | kuanrmunda | 3 | 3 | 1 | 0 | 2 | 1 | 3 | 3 | 9 | 9
246 | Sundargarh | Rourkela | lahunipada | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 8 | 8
247 | Sundargarh | Rourkela | lathikata | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11
248 | Sundargarh | Rourkela | nuagaon | 7 | 7 | 4 | 2 | 4 | 3 | 7 | 7 | 6 | 6
249 | SAMBALPUR | SAMBALPUR | bamara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
250 | SAMBALPUR | SAMBALPUR | dhankauda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
251 | SAMBALPUR | SAMBALPUR | jamankira | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5
252 | SAMBALPUR | SAMBALPUR | jujumura | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 4 | 4
253 | SAMBALPUR | SAMBALPUR | maneswar | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 4
254 | SAMBALPUR | SAMBALPUR | naktideul | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
255 | SAMBALPUR | SAMBALPUR | rairakhol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
256 | SAMBALPUR | SAMBALPUR | rengali | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
257 | Sonepur | Sonepur | birmaharajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
258 | Sonepur | Sonepur | dunguripali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
259 | Sonepur | Sonepur | sonepur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | Sonepur | Sonepur | tarva | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
261 | Sundargarh | Sundargarh | balisankara | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 10 | 10
262 | Sundargarh | Sundargarh | bargaon | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 2 | 4 | 3
263 | Sundargarh | Sundargarh | kutra | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0
264 | Sundargarh | Sundargarh | lephripara | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 10 | 10
265 | Sundargarh | Sundargarh | rajgangpur | 6 | 6 | 2 | 6 | 0 | 6 | 6 | 6 | 6 | 6
266 | Sundargarh | Sundargarh | subdega | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9
267 | Sundargarh | Sundargarh | sundargarh | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4
| TOTAL |  |  | 360 | 360 | 202 | 276 | 57 | 327 | 353 | 360 | 1132 | 944
| Message Template: | GPHQ Project Status: XX Nos of source not done.XX projects to be tendered.XX workorder to be issued. XX not completed. Please Expedite 2nd Village Status:XX Nos. of source not done against XX sanctioned.